## TechXYZ_Risk_Matrix
Risk | Likelihood (1-5) | Impact (1-5) | Risk Score | Treatment Plan
S3 bucket misconfiguration leading to public data leak | 3 | 5 | 15 | Implement least-privilege IAM, block public access at account level, enable S3 access logging, and run regular cloud security config scans.
Ransomware on employee laptops impacting access to admin tools | 3 | 4 | 12 | Deploy EDR on all endpoints, enforce automatic patching, restrict local admin rights, and maintain tested backups of admin systems.
Compromised admin account via phishing | 4 | 5 | 20 | Enforce MFA on all admin and privileged accounts, provide quarterly phishing simulations, and enable conditional access and anomaly detection alerts.
Data loss due to accidental deletion in production database | 2 | 4 | 8 | Implement automated daily backups and point-in-time recovery, restrict delete permissions, and test restore procedures quarterly.
Unauthorized third-party app access via OAuth | 3 | 4 | 12 | Limit which apps can connect via OAuth, implement app review/approval, and monitor for unusual token activity.
Insider misuse of customer photos by support staff | 2 | 4 | 8 | Enforce role-based access, log all access to customer content, implement just-in-time elevation for support, and perform periodic access reviews.
DDoS attack causing platform downtime | 3 | 3 | 9 | Use CDN and WAF protections, enable rate limiting and autoscaling, and create an incident response playbook for availability attacks.
Weak password hygiene by end users | 4 | 3 | 12 | Enforce minimum password complexity, encourage passphrases, offer/require MFA for high-risk actions, and monitor credential stuffing attempts.